## Q&A's sector
Q&A log on offshorewind.rvo.nl - Tender Hollandse Kust (west) Wind Farm Zone
Last update: October 15th, 2021
Number | Page | Subject | Sub subject | Question | Date response | Response
16 | Soil | Sample Preservation | Condition and description of the spare samples | Would it be possible for you to provide additional information in relation to the following points with regards to the geotechnical works: 1) The overall condition of the spare samples preserved for the winning bidder (i.e. that these are indeed relatively intact/undisturbed). 2) The spare samples description (i.e. if any description was undertaken before these samples were preserved over and above what is already on the geotechnical borehole logs). | 2021-10-15 | Remaining sample material consists of undisturbed (waxed) samples and disturbed (bagged) samples. See overview of remaining sample material under item 5 at; Offshorewind.rvo.nl: Data - Digital Deliverables Geotechnical Borehole Locations - Fugro. Please refer to Offshorewind.rvo.nl: Long Term Storage Soil Samples HKW (September 20, 2021) for details on 1) storage conditions during the laboratory testing phase, and 2) specifics on long-term storage of samples. Overall condition of remaining sample material has not been checked prior to transport from Fugro Wallingford to the long-term storage facility. Sample descriptions of remaining samples specifically, have not been prepared. In general, sample descriptions can be found in the geotechnical reports, on plates titled ‘Laboratory Classification Test Results’.
15 | Soil | Soil samples | Long Term Storage Soil Samples | Can you inform us on the (relevant) storage conditions of the HKW samples a) during testing and b) after testing program (awaiting handover to permit holder)? | 2021-09-20 | During and immediately after testing, undisturbed samples are stored in cold rooms in the temperature range of 8 degC to 12 degC. Disturbed samples are kept frost-free in Fugro’s warehouse, typically in a temperature range of 15 degC to 25 degC. After testing, long term storage is at a third party underground facility at a constant temperature of 14 degC.
14 | Soil | Extension Area GIS file | Soil Province Layers | We noticed in the Extension Area GIS file that there are 4 Soil Province layers (3,4,5 and 7), related to the Geotechnical Parameter Report. These are not provided in the GIS Geological Ground Model. Can you share the GIS file for the Soil Provinces? | 2021-07-22 | The Soil Provinces of the Geotechnical Parameters GIS file can be found here and is also part of the Combined Subsurface Viewer Model. Please note that the Extension Area GIS file, published separately on https://offshorewind.rvo.nl/soilw, provides the provinces for the Extension Area.
13 | General | Wind measurement campaign | Continuation of measurement campaign | In light of the now communicated HKW tender opening Q1 2022, will the wind measurement campaign continue at HKW to increase the period of wind measurements available to support the wind resource and energy yield assessments required? | 2021-07-12 | No. The metocean measurement campaign was executed for 24 months (Feb 2019 – Feb 2021). It was not scheduled to extend the period of measurements. The final delivery of the 24 months data and reports will be in Q3 2021.
12 | General | Bird and bat mortality | Mitigating measures | What will be the energy loss caused by mitigating measures to reduce bird and bat mortality for offshore windfarms? | 2021-06-30 | The response being too extensive for this Log, we would like to refer to the website: Offshorewind.rvo.nl: Mitigating measures to reduce bird and bat mortality (June 30, 2021)
11 | Soil | Soil samples | Availability of soil samples | Regarding the existing soil samples from the Geotechnical investigations by Fugro: are soil samples still available for further advanced lab testing after tender award? | 2021-06-29 | Remaining sample material will be handed over to the winner(s) of the permit tenders HKW. Reference is made to the overview of sample material in Appendix 3 of Offshorewind.rvo.nl: Report – Geotechnical Borehole Locations HKW - Fugro. The file can be found under item 5 at: Offshorewind.rvo.nl: Data - Digital Deliverables Geotechnical Borehole Locations - Fugro, so following the path; \HKW_20201020_FNLM_Digital Deliverables Geotechnical Borehole Locations _V03_F\05 HKW_20201016_FNLM_BH_SUM_XLSX_V08_F.7z\05 BH - XLS SUM\02 Overview Remaining Sample Material\. In the case that there are two different winners of the HKW permit tenders, the samples will be split per Wind Farm Site. Please note that for this splitting a lead time of 5 weeks is anticipated. RVO supports that after the permit holder has made use of remaining sample material, the sample material will be made available for scientific purposes for which results are to be disclosed in the public domain.
10 | Soil | Kingdom Files | Re-establishing links | We experience difficulties in re-establishing links in the IHS Kingdom delivery (among others on the HKW ’ Ground Model and Synthetic CPTs’ flash drive) to SEG-Y files. | 2021-06-29 | Please find hyperlinked guide to reconnect IHS Kingdom projects, created using SeismicDirect, to SEG-Y files. This is a Fugro internal working instruction which can be used by other users as well.
9 | General | Tip height | Maximum tip height | What is the correct maximum tip height? | 2021-04-12 | There was a correction made in the English translation of the draft Wind Farm Site Decisions VI and VII. The maximum tip highest level is 304 metres above sea level (MSL). Not 251 metres.
8 | General | Pipeline maintenance | Frequency of pipeline maintenance | What is the expected frequency of pipeline maintenance in the Wind Farm Zone and what is the expected maintenance time? | 2021-04-12 | Pipeline operator Wintershall Noordzee B.V has indicated the following frequency of planned surveys: Expected maintenance time varies from a few hours to a day. However, if the pipelines become exposed due to the influence of the wind farms, the frequency of surveys could change in the future. | https://offshorewind.rvo.nl/questions/view/55040885/pipeline-maintenance-in-the-wind-farm-zone-april-12-2021
7 | General | Boundaries and Coordinates | Difference in coordinates | Is there a difference between the coordinates presented in the draft Wind Farm Site Decisions for HKWWFS VI / VII and the Memo Boundaries and Coordinates HKWWFZ? | 2021-04-12 | Please note the coordinates in the Memo Boundaries and Coordinates HKWWFZ are complete and final and will also be published in updated draft Wind Farm Site Decisions for HKWWFS VI and VII. Only the coordinates and boundaries in the final Wind Farm Site Decisions are legally binding.
6 | General | Producing gas fields | Reservoir rock | Does RVO have information available about the reservoir rock of the producing gas fields for site VI and VII of Hollandse Kust (west) like depth and lateral extend of the reservoir rock? | 2021-04-12 | In the site studies of RVO no research is done on the reservoir rock. However, more information on the reservoir rock can be found on the following website: https://www.nlog.nl/kaart-velden
5 | Soil | Geotechnical data | Soil samples in digital format | The HKW reports of the geotechnical drilling also contain the detailed descriptions of the soil samples. Is it possible to disclose these digitally? For our mapping projects in the North Sea it would be very useful to also have this data. | 2021-03-16 | Laboratory Classification Test Results are disclosed at Offshorewind.rvo.nl: Data - Laboratory Classification Test Results - Fugro
4 | Soil | Geotechnical data | Data of Parameter report | With reference to Question 22 of the Q&A from Webinar Ground Model, Geotechnical Parameters and Synthetic CPTs: Would it be easy for Fugro to produce the digital LE, BE and HE in digital format because it would be very helpful in future or a retrospective update / variation to HKW? Particularly considering the increasing amount of automation and aim to increase engineering efficiency. | 2021-03-16 | Digital data of the Geotechnical Parameter report is now available at Offshorewind.rvo.nl: Data - Geotechnical Parameters HKW - Fugro
3 | Soil | Geotechnical Survey | Borehole Data | Where can we obtain borehole data from the Dinoloket, as referred to in the geophysical interpretative report? | 2020-08-20 | Borehole data from the Dinoloket can be obtained through https://www.dinoloket.nl/en/subsurface-data. Borehole data from the RVO geotechnical survey is planned to be disclosed Q4 2020.
2 | Wind and Water | Metocean Campaign | Lidar Buoys | What kind of LiDAR buoys are being used for the metocean measurement campaign, and which colour do they have? | 2019-07-25 | In the IALA system the LiDAR buoys are referred to as ODAS (Ocean Data Acquisition Systems). These buoys are yellow and carry a yellow light to indicate that they are not shipping lane markings. In addition, the light follows the ‘FI.5 (20s) flashing sequence’ to distinguish from nautical marking.
1 | General | Vertical Reference System | LAT vs NAP | The vertical reference system used for Dutch sites and the site investigations is LAT. Can you explain why LAT was selected rather than NAP? | 2019-02-18 | LAT is used as a vertical reference for most of the site studies executed by RVO.nl (ETRS89 is used as the three-dimensional coordinate system) since this is the reference level most often used and commonly accepted. Exceptions are the studies and campaigns where explicitly stated different. In that case often MSL is used as a reference. Please find a conversion table to different (mean) astronomical tide levels at the HKZ and HKN site in chapter 9.2.2. of the metocean desk study. Normaal Amsterdams Peil (NAP) is not used by RVO.nl but NAP comes close to MSL.